**CLIx Call**

**20/01/2023, 4:30 PM**

Topic: CLIx Fortnightly Call

Join Zoom Meeting

<https://zoom.us/j/93311747305>

Meeting ID: 933 1174 7305

**Agenda**

# (1) Updates

## A. Regular Activities

### I. States

(i)*Chhattisgarh*

1. Key Performance indicators as per LFA | *Updated by:*

| **KPI** | **Activity Description (including number of days)** |  **Target for October**  | **Achievement** | **Evidence** |
| --- | --- | --- | --- | --- |
| Principals Training(Quarter Four ) | Principal Orientation had happened in two ( Balod & Mungeli ) districts1. Mungeli - 3 Days
2. Balod - 2 Days
 | Nothing | Orientation of TISS, CLIx, RTICT status and Scale, Orientation on ICT lab maintenance & procurement of ICT lab & Smart Class Data. | ICT Lab Status |
| Sectoral Officers Training | **Not proposed** | **Nothing** | **Nothing** | **Nothing** |
| Resource Persons Training | **Not proposed** | **Nothing** | **Nothing** | **Nothing** |
| Training as Technology Experts | **Not proposed** | **Nothing** | **Nothing** | **Nothing** |
| Teacher Trainings**(Quarter Four )** | First batch of RTICT RPs conducted district level training in ambikapur. 138 teachers had attended this training. Online training orientation conducted in Raigarh. (Attended 50 out of 94)  | * Training for **Balodabazar** is proposed for 20th January.
* Training in DIET **Bastar** is proposed for 27th and 28th January.
 |  |  |
| Student Outreach |  |  |  |  |
| Infrastructure/ Functional Labs or School ICT Readiness | Data of ICT Infra from RTICT RPs School, both batches is procured.  |  |  | [**https://tinyurl.com/ys7uzwbt**](https://tinyurl.com/ys7uzwbt) |
| Schools Usage/Rollout Evidence |   |  |  | [**https://tinyurl.com/5vptfzvd**](https://tinyurl.com/5vptfzvd) |
| Extension of Current MoU Update (2023-28) | Letter is on Director's Table. After his signature a visit to Mantralaya will be made.  |  |  |  |
| Presentation to Education Sec.  | PPT is developed and reviewed.  |  |  |  |
| RTICT 2023 | New RTICT Cohort application form is under review process. |  |  |  |
| Endline Study | *Date to be discussed*  |  |  |  |
| Visit to Korba  | Pre- service teacher training (200) in collaboration with DIET- Korba DIET Korba is convinced to include the program in AWP of the Next FY for teacher training. School Visit: The school teachers were oriented on CLIx OERs and they showed interest for trainings The list of RTICT RPs has been shared with the DEO office and DIET Korba.The DEO office and DIET Principal is interested in forming a district steering committee  |  |  |  |

**For District Level Teacher Training and possibilities beyond:**

**DIET Korba:** Ready/On board to do pre-service teacher trainings - Next Year AWP

Discussion with RPs for understanding their experience and accordingly make future plans for the districts

To decide - Who all will be in Steering Committee - Decision to be taken by BRC Office, DIET Principal and Shweta

Schools visited in Korba: 1. SAGES: Infrastructure is good. Special attention by the Government.

2. Prayas School - Faculty from Kota to prepare students for competitive exams. Infrastructure will be in place soon.

2. Evidences (for LFA) | *Cross Verification of teacher training numbers done by*:

<https://docs.google.com/spreadsheets/d/1pPB11mA8d2txeB3_pUQ3CVObgJZSmmzY-ZrwJSDMwTM/edit#gid=0>

<https://docs.google.com/document/d/1k5i_7Sxilqah5NzAL8dw3HJRkiobGfq7/edit?usp=share_link&ouid=103298037745551739098&rtpof=true&sd=true>

3. Challenges |

(ii) Telangana

1. Key Performance indicators as per LFA | *Updated by:*

| **KPI** | **Activity Description (including number of days)** |  **Target for October**  | **Achievement** |
| --- | --- | --- | --- |
| HM Training | N.A. | N.A. | N.A. |
| Sectoral Officers Training | N.A. | N.A. | N.A. |
| Resource Persons Training | N.A. | N.A. | N.A. |
| Training as Technology Experts | N.A. | N.A. | N.A. |
| Teacher Trainings | N.A. | N.A. | N.A. |
| Student Outreach | **Erstwhile Warangal - 2731 (On CLIx staff visits)** |  |  |
| Infrastructure/ Functional Labs |  |  |  |
| Schools Usage |  |  |  |

2. Evidences (for LFA) | *Updated by:* Raju Sambri

<https://docs.google.com/spreadsheets/d/1blmL_n8w6p4R7A6u9Ns0xujZFd-mm9Mu_Ua-rVUD7NI/edit#gid=0>

3. Challenges:

4. Other Activities related to Phase 2.0

* End line after Republic Day.
* Rollout is happening. Motivation for Teachers - Whatsapp groups, Interaction with Teachers and HMs, Regular touch with schools, Education Officials also nudging them

(iii) Mizoram

1. Key Performance indicators as per LFA | *Updated by:*

| **KPI** | **Activity Description (including number of days)** |  **Target for October**  | **Achievement** |
| --- | --- | --- | --- |
| HM Training | **N.A** | **N.A** | **N.A** |
| Sectoral Officers Training | **N.A** | **N.A** | **N.A** |
| Resource Persons Training | **N.A** | **N.A** | **N.A** |
| Training as Technology Experts | **N.A** | **N.A** | **N.A** |
| Teacher Trainings | **N.A** | **N.A** | **N.A** |
| Student Outreach |  |  |  |
| Infrastructure/ Functional Labs |  |  |  |
| Schools Usage |  |  |  |

1. Evidences (for LFA) | *Updated by:*

<https://docs.google.com/spreadsheets/d/115MonmyAUWw68eILCbbHXFTW9UNwBdP51wbnSAMS-Zg/edit#gid=0>

1. Challenges |

 1 school is still pending for lab setup and roll out.

Mizoram: HCL experience

* Pranjal and video team - video shooting - school was quite cooperative
* Overall good experience
* Pranjal - 1 school Teacher interaction and 1 for roll out - he was quite happy
* Define things well in MoU
* Rk says WE WILL GET IT!!!

### II. Tech Update

(i) CLIx OERs:

1. SCERT Poster and Blog: Updates (Only 10 days to left)

2. Website Updates: will share

### III. Research

#### (i) FGD Plan and Timeline

Tool: <https://docs.google.com/document/d/1cA46Wsj92XTWPiq7ZsTDv0wzOh4DrXAap8-UvpqOxIA/edit>

* To document teachers' experiences with CLIx modules, platform and tools and students' engagement with the same.
* Around 40-45 min discussion
* Teachers who are engaged with us since Phase I would be preferred as they will have more stories to share about students' experiences (since in this Phase roll out happened quite late) and about their preparedness when COVID struck
* A school that has more than one teacher engaging with CLIx will be nice but not compulsory
* Can go to individual interviews
* Minimum 3 teachers - each one reach one
* Ideal: close by Feb end

Timeline: To discuss with the teams

TS:

CG:

MZ:

#### (ii) End Line Study

* Tool shared for Printing
* Confirmation of mailing addresses
* Since next week is Republic Day maybe conducting the endline post that would be good

Mizoram - Endline for two schools

### IV. Platforms and Social Media

#### (i) Website Updates

No updates from Diksha’s side (Ramesh is quite occupied with other tasks so haven’t had a word with him regarding infographics)

#### (ii) Organization of Videos on YouTube Channels

Have begun. Listing videos under different themes.

### V. Data Archival

* No update on the assigned task. Will try to work over the weekend. Anyone want to volunteer?

## B. New Activities

### I. CLIx Assam

* No new updates that I am aware of (Diksha)

### II. CLIx Tamil Nadu

* Discussion in progress

# (2) Issues/ Themes for Documentation and Discussion

I. Data Archival Updates from the Meeting held on 11th Jan 2023: Platform to host the data archival on

* Selected 4 platforms based on [certain affordances](https://docs.google.com/document/d/1rooc1C-oKy_EKXY5vuSfQEDIBAMbHBth1gbVBeu3X8c/edit):
	+ INVENIO <https://103.36.84.199:4443/>
	+ DATAVERSE = <http://103.36.84.199:8082/>
	+ CKAN = <http://103.36.84.199:5000/>
	+ DMS = <https://dms.tiss.edu/jspui/>
* These 4 platforms will be tested and piloted with the couple of projects data which is currently available and structured for this purpose
* Based on experience and feedback, the one of four will be finalized and made available for the DA process.

II. Considerations or the plan of action about using Guidebook platform (<https://clixguidebook.tiss.edu/>)

III. General Discussion about ]Documentation and further Plan

* Anusha Mam’s [notes](https://docs.google.com/document/d/1ujFIfkfihMbCld4Gq65SfDvBgKewMKONx_WSM_dTcjI/edit)

IV. Discussion on Samples of Audio/Video/Photos uploaded by TS team with regards to Themes discussed and Plan for Chhattisgarh

IV. CLIx Platforms and Websites - Beyond March 2023

* A dedicated meeting for CLIx belongings beyond March 2023
* People who should at least be part: All the PIs, Tech Team Members, Diksha, Sadaqat and Satej
* Mid of Feb?
* Agenda needed

# (3) Asks/ Announcements

* 23-25 Sadaqat Sir will be in Hyderabad - will conduct FGD (School finalized), Karthik will accompany him to the IFP school and plan to finalize the rubric.
* TS: CL4 STEM team in Feb end (23-25 Feb) - Planning in process; Demonstration of rollout and meet district level officials, sightseeing etc.
* TS: Sanjay Shah, Deputy Registrar, visiting ZPHS Kukatpally school in Ranga Reddy on 23rd Feb. Agenda: to see the work on ground
* Satej Sir is quite intrigued about things happening in Telangana :P .
* TS: IFP - 3 schools selected for Pilot. Curation of OERs at this stage only for Pilot but later for the whole curriculum. Development of Rubric in process - being developed with a larger objective in mind.

*Karthik concerned about maintenance of IFP from his experience with CLIx labs*

* TS: Shaala Siddhi getting traction - Gauging the situation in terms of infrastructure/ resources, gaps in understanding and capacity building.
* TS: IFP - Tender cycle for curation isn’t complete yet. (Satej Sir - configurations, specifications and service plan). Tech specs dealt at directorate level. Demo - BenQ, Samsung and LG
* CLIx Writing Retreat - EVERYONE IS EXCITED!

# (4) Any other

# (5) Recap of To-dos